## s106-based
Matter 6 Q6.10 - Local Plan Housing Site Infrastructure & Housing Delivery Schedule for sites >100 dwellings
Site | Site | Settlement | Site | s106 | Infrastructure | Planning | Dwelling | 2018/ | 2019/ | 2020/ | 2021/ | 2022/ | Infrastructure | Housing | Infrastructure | Housing | Infrastructure | Comments
Ref | Address |  | Infrastructure | Funding | Project Status | Application | Total | 2019 | 2020 | 2021 | 2022 | 2023 | Delivery 2018-2023 | Years 6-10 | Delivery 2023-2028 | Years 10-18 | Delivery Years 10-18
|  |  |  | Contrib. |  |  | at 1.4.18 | [5 empty] | Years 1-5 (2018-2023) | 2023-2028 | Years 6-10 | 2028 - 2036 | 2028 - 2036
Eastleigh / Chandlers Ford
S3(iii)a | Stoneham / Chestnut Avenue | Eastleigh | 1. FA Sports Hub | 5500000 | Building complete and in use as are the artificial pitches. Grass pitches under construction. | Various. O/15/76023 but the whole site has reserved matters / full permission. | 1131 | 100 | 120 | 150 | 150 | 150 | FA Sports Hub - open | 461 |  | 0 |  | Site permitted and well underway. O/12/71514 and subsequent reserved matters. NB scheme developing more quickly than shown in the trajectory; largely as a result of EBC involvement
|  |  | 2. Community Building | 1175000 | EBC delivering. Scheme approved. Imminent start
|  |  | 2. Community Ancillary | 400000 | [8 empty] | Mainly revenue expenditure
|  |  | 3. Education Provision | 5500000 | Primary School to open Sept 2020. Under construction | [7 empty] | Stoneham Park Primary Academy to come on stream 2020
|  |  | 4. Affordable Housing Contribution | 1425000 | [8 empty] | Affordable Housing
|  |  | 5. Health Contribution (ETC) | 225000 | Delivery still under review. ETC
|  |  | 6. Lakeside CP Extension & Maintenance | 413000 | Complete | [7 empty] | Lakeside extension
|  |  | 7. Offsite highway contribution | 860000 | Stoneham Lane works complete | [7 empty] | Offsite Highway Works |  |  |  |  | £4.9m of external funding from the FA, Premier League & Sport England
|  |  | 8. Public Art / Public Realm (inc ETC) | 431000 | Underway onsite
|  |  | 9. POS / Play | 409650 | Play area laid out. Equipment to be installed early 2020 | [7 empty] | Phased with development
|  |  | 10. SINC / Access Management | 800000 | Home Wood. SANG role. Project underway | [7 empty] | Phased with development
|  |  | 10. Other | 1406970
|  |  | Local Centre |  | Discharge of conditions. Construction to commence early 2020 | [7 empty] | Permission for local centre etc granted 14th March 2019 (RM/18/84537)
DM24. 18 | Draper Tools | Chandlers Ford | 1. On site Open space & maintenance | 130869 |  | O/10/66978 granted 24.07.12. RM/17/83628 granted 31.1.18 | 140 | 0 | 0 | 0 | 20 | 30 |  | 90 | Phased with development | 0
|  |  | 2. Off-site open space contribution | 18851 | [10 empty] | Phased with development
|  |  | 3. 60-70 bed care home | [11 empty] | Phased with development
|  |  | 4. Community infrastructure contribution | 188940 | [10 empty] | Phased with development
Bishopstoke / Fair Oak / Horton Heath
DM24. 2 | The Mount Hospital | Bishopstoke | 1. Affordable housing contribution | 956122 | Prior to commencement. Paid. To be delivered off site | O/12/71007 and subsequent reserved matters | 75 | 22 | 53 | [8 empty] | Residue of larger allocation underway. 142 completions achieved 2015-2018. 20 under construction at March 2018. Permission granted for Phase 3 (F/17/80513) 1.2.18
|  |  | 2. Off site sustainable transport contribution | 40000 | Paid. | [7 empty] | Dropped kerb, tactile paving and works to bus shelters in Bishopstoke area implemented
|  |  | 3. Public Art contribution | 25000 | Paid and project installed on site | [7 empty] | Art provided on site
S3 (ii) / HH1 | West of Horton Heath | Horton Heath |  |  | No progress on implementation on any of these as these commitments were associated with the two original outline applications as applied for by Drew Smith. EBC has since bought the sites and is currently re-planning the areas as a single new community. | Outline permissions | 1500 | 0 | 0 | 75 | 145 | 154 |  | 250 |  | 876 |  | Note that these provisions are based on the s106 agreements for the two permitted schemes. The council has subsequently purchased the site and will be re-planning the whole development. The secondary school will not now be provided (it is being provided in association with HE2). The other provision are included as an indication of what might be expected from the WoHH in general terms. c£10m of external funding from the Housing Infrastructure Fund MVF towards the cost of the Bubb Lane / Burnett's Lane Link and also the Allington Lane Link. Further c£10m of funding from the LA Accelerated Construction fund
1. Chalcroft Permission |  |  | 1. Primary Education contribution | 5876700 |  | 950 dwellings Chalcroft Farm O/14/75735 | [6 empty] | Horton Heath new Primary Academy delayed due to new ownership and masterplanning etc
|  |  | 2. Secondary education contribution | 4757876 | [8 empty] | See Woodhouse Lane below.
|  |  | 3. Community development worker contribution | 100000
|  |  | 4. Southern Damselfly Habitat Mitigation contribution | 95000
|  |  | 3. Allotment contribution | 95000
|  |  | 4. Health facilities contribution | 145666
|  |  | 5. Public Art contribution | 443500
|  |  | 6. j7 M27 contribution | 150000
|  |  | 7. SRMP contribution | 72400
|  |  | 8. TRO costs | 450000
|  |  | 9. Offsite highway works contribution | 735349.98
|  |  | 10. Onsite POS contribution & fees | 112351.5
|  |  | 11. Named junction improvements | 227590
|  |  | 12. Air quality monitoring contribution | 15000
|  |  | 13. Onsite play area contribution & fees | 1423700
Provision of £10.42ha secondary school site
Provision of local centre
Provision of community building
Provision of 13.24ha of ecological mitigation land
Provision of 18.96ha of POS and 3.3ha sports pitches
Provision of Bubb Lane / Burnett's Lane Link Road & Allington Lane / Fir Tree Lane Link
Public bus service subsidy for 8 years from 100th occupation (or3 years after occupation of final dwelling)
2. Fir Tree Lane Permission |  |  | 1. Primary education contribution | 2783700 |  | 450 Fir Tree Farm O/16/79354
|  |  | 2. Secondary education contribution | 2253731
|  |  | 3. Offsite highway works contribution to name junctions | 1180930
|  |  | 4. Health facilities contribution | 69000
|  |  | 5. PROW contribution | 62000
|  |  | 6. Onsite POS inc maintenance | 421763
|  |  | 7. Play area contribution | 190200
DM24. 25 S3(iii)f in ED32 | Pembers Hill Farm | Fair Oak | 1. Primary education contribution | 1350000 | 50% prior to occupation of 100th dwelling. 50% prior to occupation of 200th dwelling | O/15/77190 and subsequent reserved matters RM/18/83278 granted 28.22.18 | 242 | 0 | 50 | 50 | 50 | 42 |  | 50 |  |  |  | Site fully permitted and under construction.
|  |  | 2. Secondary education contribution | 2825000 | 50% prior to occupation of 100th dwelling. 50% prior to occupation of 200th dwelling
|  |  | 3. Local highway improvements | 1520000 | Prior to occupation | [7 empty] | Named local junction, highway and footway improvements
|  |  | 4. Other transport / travel plan | 126000 | Prior to occupation | [7 empty] | As above
|  |  | 5. Health facility contribution | 95000 | 50% on commencement. 50% on occupation of 100th dwelling | [7 empty] | Towards Stokewood or new provision in local area arising out of SGO
|  |  | 6. Local environmental improvements | 30000 | 50% on commencement. 50% on occupation of 100th dwelling | [7 empty] | Various in FO Village Centre
|  |  | 7. Local community infrastructure contribution | 339000 | 50% on commencement. 50% on occupation of 100th dwelling | [7 empty] | Extensions and improvement to existing facilities in Fair Oak
|  |  | 8. On and off-site POS & PF inc maintenance | 662000 | Offsite to be paid on commencement. Onsite prior to occupation of 220th dwelling | [7 empty] | Offsite to be used at West Horton playing fields or anything arising out of SGO
|  |  | 9. Public Art contribution | 50000 | 50% prior to commencement. 50% prior to occupation of 100th dwelling
|  |  | 10. SuDS maintenance | 214000 | Payment linked to SUDS adoption land transfer
326 | Crowdhill, Winchester Road | Fair Oak | 1. POS inc. equipment, maintenance & admin | 303774 | Installed | O/13/73707 and subsequent reserved matters | 115 | 100 | 15 |  |  |  | Payments phased with development. Development to be complete within the 5 year period. All commitments to be met within that period. |  | Installed |  |  | Site of 330 dwellings. Now almost if not totally complete at November 2019
|  |  | 2. Primary education contribution | 589135 | Improvements to FO Infant School
|  |  | 3. Secondary education contribution | 1944664 | Imps to Wyvern College
|  |  | 4. Public Art Contribution | 70000 | Paid. Art installed onsite | [9 empty] | Art installed
|  |  | 5. Offsite transport contribution & travel planning | 1457096 | Named junction improvements | [9 empty] | Junctions improved
|  |  | 6. Provision of community building | - | Built and in use | [9 empty] | Built
Hedge End / West End / Botley
S3(iii)d | North & East of Boorley Green | Botley | 1. Community Building & Changing Rooms | 2023560 | Prior to occupation of 600th dwelling | Various existing permissions. O/12/71514 but whole site has reserved matters / full permission. | 1259 | 210 | 180 | 180 | 180 | 180 | All key triggers within the 5-year period | 329 |  | 0 |  | Site under construction with >100 dwellings complete
|  |  | 2. Education Contribution | 7047601 | Within 9 months of occupancy of 150th dwelling. HCC schedule Boorley Park 2FE Primary to come on stream 2020. School built and opened early
|  |  | 3. Health (GP Improvements) | 255000 | Prior to occupation of 150th dwelling - paid
|  |  | 3. Offsite Highway Improvements | 530000 | 50% paid on occupation of 150th dwelling. 50% outstanding (350th)
|  |  | 4. M27 j8 Contribution | 221000 | Prior to occupation of 350th dwelling
|  |  | 5. POS & Play inc Maintenance | 1071951 | Ongoing - phased with development
|  |  | 6. Public Art | 100000 | Ongoing. Steering group established
|  |  | 7. SINC & Woodland Maintenance | 1375950 | Prior to completion of 350th dwelling
|  |  | 8. SRMP Contribution | 144800 | Prior to 1st occupation
|  |  | 9. Botley Footpath Works | 274000 | Complete
|  |  | 10. Economic Development | 100000 | Paid
|  |  | 11. HWRC | 95000 | Prior to occupation of 200th dwelling
|  |  | 12. Other | 850880
|  |  | Sundays Hill Bypass & Maypole Roundabout | ? | Maypole complete (1st occupation) Sundays Hill 350th dwelling
|  |  | Bus Service Subsidy 15 years | ? | 15-year period to start prior to 1st occupation. Underway
|  |  | New Local Centre? | ? | Resolution to permit R/16/79505 22/5/17 but new application expected
HE2 | St John's Road | Hedge End | 1. Community infrastructure contribution | 131100 | Part paid, part 50th occupation | F/15/76804 Phases 1 & 2, F/17/80651 for Phase 3 | 167 | 60 | 45 | 45 | 17 |  | All to be delivered within the five year period |  |  |  |  | This site comprises Phase 2 to the adjacent site to the north (DM24) as identified on the submitted Policies Map. Together they will deliver the extension of the Sundays Hill bypass to St John's Road. Phase 1 (DM24) is almost complete. Both Phases are fully permitted.
|  |  | 2. Offsite POS / Playing Fields Contribution | 129969 | Part paid, part 50th occupation
|  |  | 3. Offsite POS / Play contribution | 70797.54 | As above
|  |  | 4. Offsite local greenspace contribution | 23230.84 | Paid
|  |  | 5. Offsite wet woodland contribution | 240000 | Paid
|  |  | 6. Offsite POS maintenance & fees | 27268.64 | Paid
|  |  | 7. Public Art contribution | 36600 | ?
|  |  | 8. Reptile receptor management | 9524 | Complete
|  |  | 9. Secondary Education contribution | 510846 | Prior to commencement
|  |  | 10. SRMP contribution | 18656 | Prior to commencement
|  |  | 11. Sustainable transport contribution. Improvements to named local junctions | 380000 | Prior to 1st occupation
|  |  | 12. Travel Plan sum inc fees | 80218 | Paid
|  |  | 13. Woodland maintenance | 25753.71 | Paid
|  |  | 14. Provision of link road extension |  | Part u/c
HE1 | West of Woodhouse Lane | Hedge End | AQ Monitoring Contribution | 67385.63 |  | O/18/83634 granted 6.9.19 | 605 | 0 | 0 | 20 | 30 | 50 |  | 500 |  | 5 |  | Decision issued 6th September 2019. The County Council as education authority has an urgent need to establish the new secondary school to open at the beginning of the academic year in 2021. The other contributions are phased with phases of the development meaning the majority will have been paid within the first five year period. Most of the contributions are required to have been paid in full by the time of occupation of the 300th dwelling (i.e. within the five years). The exception is the delivery of the local centre which is required by occupation of the 350th dwelling.
|  |  | 1. Bridge Structure Contribution | 434721
|  |  | 2. Bus Service & Infrastructure Contribution | 453000
|  |  | 3. Community Infrastructure Contribution (sports hub) | 1166735.15
|  |  | 4. Community development worker contribution | 83255.56
5. Land and prep works for Play areas
|  |  | 6. Play area contribution & maintenance | 351439.11
|  |  | 7. Early Years education contribution | 400000
|  |  | 8. SEND contribution | 533013
|  |  | 9. Health contribution to CCG | 94906.48
|  |  | 10. New PROW contribution | 318080
|  |  | 11. Onsite POS maintenance (+7.5ha of land) | 1095304
|  |  | 12. Public Art contribution | 258888.52
|  |  | 13. Offsite POS and play area improvements | 444626
|  |  | 14. District Park / Playing Fields contribution | 1507379
|  |  | 15. Route 6 bridleway contribution & extension | 134856
|  |  | 16. SINC land contribution | 856849
|  |  | 17. SRMP contribution | 373536.06
|  |  | 18. Provision of 7FE secondary school on 9.7ha of land + PFs | [9 empty] | Deer Park 7FE Secondary Academy to come on stream 2021
19. Provision of new 1,000m2 local centre
BO2 | Uplands Farm | Botley | Public open space |  |  | O/18/83698. Resolution to permit 28.01.19 | 375 | 0 | 0 | 0 | 0 | 20 |  | 230 | Most of the infrastructure ls likely to be delivered during this 'medium term' period. | 125 |  | Committee resolution to permit 28.01.19. No planning permission issued yet. So, no s106 agreement. HCC is focussing efforts on early delivery of Woodhouse Lane due to the urgent need to deliver the secondary school. Hence phasing of this development into the medium term. The list of infrastructure identified in this table is taken from the Council Officer's report to the committee which issued the resolution to grant in January 2019. The nature and extent of infrastructure identified is consistent with other major schemes identified in this table albeit that costs cannot be attributed at this stage. c£10m of funding secured from the Housing Infrastructure Fund MVF towards the cost of this £26m project
Improvements to allotments
New allotments
|  |  | Botley Bypass |  | CS/17/81266 consented by HCC 15.11.17 | [9 empty] | Latest HCC Botley Bypass update November 2019. The County Council is currently progressing with the detailed design and land acquisition for the scheme, and will be looking to start construction work in Woodhouse Lane in 2020. Works to construct the bypass are likely to follow on in 2020/21.
Primary Education contributions (Botley CE primary)
Secondary education contributions (Deer Park Secondary)
SEND contributions
Employment contribution in lieu of provision
Possible undergrounding of power lines
POS inc Community Orchard
Offsite highway works
Railway bridge pedestrian improvements
Winchester Street footway enhancements
PROW enhancements
Public transport contributions (enhanced bus service)
Air Quality Monitoring contribution
SRMP contribution
Community development worker support
Community health contribution
Ecology mitigation / buffers
S3(iii)e | NW Boorley Green / Hedge End North | Botley | 1. Playing pitch and play areas inc maintenance | 576342 | To be paid in thirds starting on 1st occupation | O/15/75953 and subsequent Reserved Matters | 680 |  | 50 | 150 | 150 | 150 |  | 30 |  |  |  | Original outline O/15/75953. Phase 1 (301 dwellings) permitted 16.01.19 (RM/17/81628). Phase 2 (143 dwellings) submitted 16.11.18 (RM/18/84466). Pre-app for Phase 3 (236 dwellings) submitted June 2019
|  |  | 2. Community Infrastructure Contribution | 804916 | To be paid in thirds. Final payment on occupation of 100 dwellings
|  |  | 3. Health facilities contribution | 137500 | Prior to completion
|  |  | 4. M27 j8 improvement contribution | 200000 | Prior to occupation of 100th dwelling
|  |  | 5. Primary Education Contribution | 5786130 | 55% to be paid on occupation of 100 dwellings | [7 empty] | Boorley Park Primary Academy to come on stream 2019
|  |  | 6. Secondary Education Contribution | 4759995 | 55% to be paid on occupation of 100 dwellings | [7 empty] | Deer Park Secondary Academy to come on stream 2021
|  |  | 7. Public Art Contribution | 261249 | Prior to 1st occupation
|  |  | 8. SRMP Contribution | 120000 | Prior to 1st occupation
|  |  | 9. Sustainable Transport/ Local Junction Improvements Contribution | 1400000 | To be paid in 4 instalments. Final instalment on occupation of 300th dwelling | [7 empty] | Named local junction improvements
|  |  | 10. Other | 440250
DM24. 38 | Land off Botley Road | West End | 1. Community infrastructure & Health Facilities contribution | 121848 |  | O/15/76418 & RM/18/82821 | 100 |  | 25 | 40 | 35 |  | Named local facility improvements |  |  |  |  | S106 agreement on Outline with Gladman. Site won on appeal. RM granted to Foreman Homes. RM/18/82821 issued 5th March 2019
|  |  | 2. Controlled parking zone contribution | 20000 | [8 empty] | Ageas bowl events mitigation |  |  |  |  | This site used to be used on an ad hoc basis for temporary parking when the Ageas Bowl was hosting major events
|  |  | 3. SSSI Mitigation contribution | 6658 | [8 empty] | Signage, fencing etc
|  |  | 4. Offsite POS contribution | 106140 | [8 empty] | Named improvements to local facilities
|  |  | 5. Primary education contribution | 505700 | [8 empty] | Enhancement of facilities at St James CE Primary
|  |  | 6. Public Art contribution | 30000
|  |  | 7. Secondary Education contribution | 699000 | [8 empty] | Contribution towards Deer Park Academy
|  |  | 8. SRMP contribution | 17600
|  |  | 9. Sustainable Integrated Transport contribution | 374000 | [8 empty] | Various named local footway, cycleway and crossing improvements |  |  |  |  | Development phased for completion within five years. All infrastructure can be expected within that period.
|  |  | 10. Travel Plan fees | 13000
Hound / Hamble / Bursledon
316 | Dodwell Lane | Bursledon | 1. Community infrastructure contribution | 400860 | Phased with development | O/12/71522, R/14/75595 (Phase 1 189 dwellings), R/15/76606 (Phase 2 61 dwellings) | 213 | 75 | 75 | 50 | 13 | [6 empty] | Development phased for completion within five years. All infrastructure can be expected within that period.
|  |  | 2. Junction 8 Improvements contribution | 39000
|  |  | 3. Manor Farm CP Contributions | 75000 | Prior to occupation of 1st dwelling
|  |  | 4. POS maintenance contribution | 220183.65 | Paid in thirds
|  |  | 5. Play area contribution inc maintenance | 82500
|  |  | 6. Public Art contribution | 72600 | On completion of 150th dwelling
|  |  | 7. Reptile translocation | 27000 | Phased with development
|  |  | 8. Scout camp relocation | 125000 | Prior to commencement
|  |  | 9. SRMP contribution | 51700
|  |  | 10. Sustainable Integrated Transport Contribution | 195000 | Kings Copse Ave junction improvements - prior to occupation
|  |  | 11. Woodland maintenance contribution | 500700 | Phased with development
320 | West of Hamble Lane | Bursledon | 1. Offsite POS commuted maintenance sum | 70461.6 | 50% 75th occupation. 50% 140th. 50% paid | O/12/71828, R/15/76830 | 114 | 70 | 44 |  |  |  | Named local improvements |  |  |  |  | Reserved matters approved 18th January 2016. Development well under way
|  |  | 2. Play area contribution inc maintenance | 80000 | Complete
|  |  | 3. Public art contribution £300pd | 45000 | 50% paid. 50% on 140th occupation | [7 empty] | Windhover roundabout Kestrel
|  |  | 4. SRMP contribution (170pd) | 25500 | Prior to occupation
|  |  | 5. Sustainable transport contribution | 581764 | 50% prior to commencement. 50% occupation of 75th dwelling | [7 empty] | Phased with development - Hamble Lane / Portsmouth Road junction / Windhover roundabout
|  |  | 6. Air Quality Monitoring contribution | 15000 | Phased with development 25% prior to commencement. 25% prior to 75th occupation. 50% prior to 140th occupation. 1st 50% paid
|  |  | 7. Community Infrastructure contribution | 225000 | 50% 75th occupation. 50% 100th occupation. 1st 50% paid
|  |  | 8. Onsite POS and play area contribution | 112500 | 75th occupation. Complete
341 | Berry Farm | Bursledon | 1. Air quality monitoring & mitigation contribution | 16670.75 | 50% paid on commencement. 50% prior to occupation of 60th dwelling | F/15/76582 | 152 | 55 | 50 | 47 |  |  | All infrastructure to be provided within the five year period |  |  |  |  | 166 dwellings. F/15/76582 granted 11th March 2016. F/17/79863 for sams granted 16th August 2017 . Development well underway
|  |  | 2. BREAM post occupation evaluation contribution | 10042.62 | 50% paid on commencement. 50% prior to occupation of 60th dwelling
|  |  | 3. Community infrastructure contribution | 265312.36 | 50% paid on commencement. 50% prior to occupation of 60th dwelling | [7 empty] | Extension & improvements to named local community facilities
|  |  | 4. Portsmouth Road / Hamble Lane junction design contribution | 80000 | Prior to commencement.
|  |  | 5. Highway works contribution | 500000 | 50% prior to commencement. 50% prior to occupation of 10th dwelling | [7 empty] | To implement the above junction works
|  |  | 6. Offsite open space contribution | 142708.68 | 50% paid on commencement | [7 empty] | Improved facilities at 3 named facilities
|  |  | 7. On site POS commuted maintenance | 97305.87 | Prior to occupation of 90th dwelling
|  |  | 8. Onsite play area contribution and maintenance and fees | 105176.12 | Linked to land transfer to EBC
|  |  | 9. Primary education contribution | 700000 | 50% prior to commencement. 50% prior to occupation of 50th dwelling | [7 empty] | For Bursledon I/J School, Freegrounds I/J school and/or Kings Copse Primary
|  |  | 10. Public Art contribution | 63775.47
|  |  | 11. Secondary Education contribution | 150000 | 50% prior to commencement. 50% prior to occupation of 50th dwelling | [7 empty] | For Hamble College
|  |  | 12. Sustainable Integrated Transport Contribution | 546645.49 | 50% prior to commencement. 50% prior to occupation of 10th dwelling
|  |  | 13. Travel Plan contribution & fees | 116990.13 | Phased with development
|  |  | 14. SRMP contribution | 29074.69 | 50% paid on commencement. 50% prior to occupation of 60th dwelling
|  |  | 15. Offsite play area contribution | 31963.43 | Paid on commencement
355 | South of Bursledon Road | Bursledon | 1. Air quality monitoring contribution | 20285.51 | 25% on 1st occupation. 25% on 50th dwelling. 50% on 100th | O/15/77121, F/18/82322 | 200 | 25 | 50 | 50 | 50 | 25 | [5 empty] | Full permission issued 29th March 2018. Work started on site summer 2018. Contributions all phased with development so will be within 5 years
|  |  | 2. Community Infrastructure Contribution | 280902.32 | 25% on occupation of 50th dwelling. 25% on 100th. 50% on 150th | [7 empty] | Pilands Wood Community Centre, Bursledon windmill and village hall access improvements
|  |  | 3. On site POS commuted maintenance | 124289.28 | Prior to occupation of 100th dwelling
|  |  | 4. Country Park Commuted Maintenance sum | 279584.9 | Prior to occupation of 100th dwelling
|  |  | 5. On site woodland planting contribution | 22821.19 | Prior to occupation of 100th dwelling
|  |  | 4. Play Area contribution and maintenance | 103759.28 | Prior to occupation of 100th dwelling
|  |  | 5. Primary education contribution | 951000 | 10% on 1st occupation. 10% on 50th. 30% on 100th. 50% on 150th | [7 empty] | Bursledon I/J School
|  |  | 6. Public Art contribution | 77934.78 | 25% on 1st occupation. 25% on 50th dwelling
|  |  | 7. Secondary education contribution | 373296 | 10% on 1st occupation. 10% on 50th. 30% on 100th. 50% on 150th | [7 empty] | Hamble School
|  |  | 8. SRMP Contribution | 36200 | 50% on 1st occupation. 50% on 50th dwelling
|  |  | 9. Sustainable Integrated Transport Contribution | 691045.7 | 50% on 1st occupation. 50% on 50th dwelling
|  |  | 10. Travel Plan fees | 69565 | Prior to occupation
Plus 10.09ha of POS inc new country park